## Winter Semester
Weeks end on Friday | WEL Water, Flood Early Warning: Time Log
[5 empty] | Total Hours | 16 | (Individual time + team time) |  | Total Hours | 13.5 | (Individual time + team time) |  | Total Hours | 15 | (Individual time + team time)
| Team |  |  |  | Hunter Williams |  |  |  | Jacob Lewis |  |  |  | Chris Edwards
| Date | Planed | Actual | Activities | Date | Planed | Actual | Activities | Date | Planed | Actual | Activities | Date | Planed | Actual | Activities
WEEK 1 | 2019-01-08 | 1 | 1 | Prepare Presentation for Class
|  | 3 | 3 | Class
WEEK 2 | 2019-01-15 | 1 | 1 | Prepare Presentation for INDRHI | 2019-01-15 | 0.5 | 0.5 | Follow up with Flood Tags |  |  |  |  | 2019-01-15 | 1 | 0.75 | Make new figures with FFG polygons
|  | 3 | 3 | Class |  | 1 | 1.5 | Explore Q-GIS
WEEK 3 | 2019-01-23 | 1 | 1 | Finalize and Practice Presentation | 2019-01-24 | 1 | 1 | Personal Prep for Trip | 2019-01-24 | 1 | 1 | Personal Prep for Trip | 2019-01-22 | 1 | 1.5 | Translate slides 6-end
| 2019-01-25 | 0.5 | 0.25 | Finalize questions for INDRHI |  | 0.5 | 0.5 | Practice Presentation | 2019-01-23 | 1 | 1 | Translate first 5 Slides |  | 1 | 1 | Personal Prep for Trip
| 2019-01-25 | 0.5 | 0.25 | PPM | 2019-01-25 | 1 | 1 | Project Management Plan |  |  |  |  | 2019-01-25 | 0.25 | 0.25 | Discuss project with Jason
|  | 2 | 2 | Class
WEEK 4
WEEK 5
WEEK 6
WEEK 7
WEEK 8
WEEK 9
WEEK 10
WEEK 11
WEEK 12
WEEK 13
WEEK 14

## Fall Semester
Weeks are Monday to Sunday | WEL Water, Flood Early Warning: Time Log
[5 empty] | Total Hours | 23 | (Individual time + team time) |  | Total Hours | 24.75 | (Individual time + team time) |  | Total Hours | 31.5 | (Individual time + team time)
| Team |  |  |  | Hunter Williams |  |  |  | Jacob Lewis |  |  |  | Chris Edwards
| Date | Planned | Actual | Activities | Date | Planned | Actual | Activities | Date | Planned | Actual | Activities | Date | Planned | Actual | Activities
WEEK 1 | 2018-09-17 | 1 | 1 | Formulate WIG's
| 2018-09-21 | 1 | 1 | Team Building Exercises
WEEK 2 | 2018-09-27 | 1 | 1 | Formulate Lead Measures
WEEK 3 | 2018-10-01 | 1 | 1 | Statement of Work | 2018-10-07 | 2 | 2 | Statement of Work | 2018-10-07 | 2 | 2 | Statement of Work | 2018-10-04 | 2 | 4 | Statement of Work
| 2018-10-04 | 1 | 1.25 | Statement of Work
WEEK 4 | 2018-10-08 | 1 | 0.75 | Statement of Work |  |  |  |  | 2018-10-15 | 0.5 | 0.5 | Status Report 2
| 2018-10-11 | 1 | 1 | Search for Useful DR Shapefiles
WEEK 5 | 2018-10-18 | 1 | 0.5 | Revised Lead Measures | 2018-10-19 | 0.5 | 0.5 | NWS Research
WEEK 6 | 2018-10-25 | 1 | 2 | Research: Forecast Data |  |  |  |  | 2018-10-22 | 0.5 | 0.5 | ONAMET Forecast Research | 2018-10-22 | 1 | 1.5 | NOAA Research, Status Report
[13 empty] | 2018-10-26 | 2 | 2 | NOAA GFS Research
[13 empty] | 2018-10-26 | 0.25 | 0.25 | Talk to Jason about data
WEEK 7 | 2018-10-29 | 0.5 | 0.5 | Prepare Presentation | 2018-10-29 | 0.5 | 0.5 | Status Report | 2018-10-29 | 0.5 | 0.5 | Scoreboard | 2018-10-29 | 1 | 1 | Scoreboard
| 2018-10-29 | 0.5 | 0.5 | Research: NOMAD Data | 2018-10-29 | 0.5 |  | Talk to Dr. Nelson and Dr. Hughes about flood tags and research flood tags |  | 0.5 |  | Talk with ONAMET | 2018-10-31 | 0.5 | 0.25 | Find time stamp of flash flood guidance
| 2018-11-01 | 1.5 | 1.5 | Research: NOMAD/Prepare Presentation |  |  |  |  | 2018-10-31 | 1 | 0.5 | Review Bulletins | 2018-11-02 | 0.5 | 0.25 | Talk to Jason about Forecast data already in app
WEEK 8 | 2018-11-05 | 0.5 | 0.5 | Scrum |  |  |  |  | 2018-11-05 | 0.25 | 0.25 | Status Report
| 2018-11-06 | 0.5 | 0.5 | Meet with Dr. Hughes
| 2018-11-06 | 3 | 1 | INDRHI Meeting
| 2018-11-07 | 1 | 1 | SOW Addition, GFS research
WEEK 9 | 2018-11-15 | 1 | 1 | GFS Searching | [8 empty] | 2018-11-12 |  | 0.5 | Status Report
[13 empty] | 2018-11-15 |  | 0.25 | GFS Searching
WEEK 10 |  |  |  |  | 2018-11-19 | 0.5 | 0.5 | Status Report
[Thanksgiving Week]
WEEK 11 | 2018-11-29 | 1 | 1.5 | Divide up 30%, GFS Searching |  |  |  |  | 2018-11-26 |  | 0.5 | Status Report
WEEK 12 | 2018-12-06 | 1 | 1 | 30% Report, Zonal Statistics |  |  |  |  | 2018-12-09 | 0.5 | 0.5 | 30% Report | 2018-12-08 | 2 | 2 | 30% Report
WEEK 13 | 2018-12-10 | 1 | 1 | Revise and submit 30% Report
WEEK 14